## Final Task
Milestone | Module | Functionality | Sub-Tasks | Member's Name | Status | Completion % | Start Date | End Date
M1 | Setup & Structure | Infrastructure Setup |  | All Team | Completed |  | 2022-11-02 | 2022-11-02
|  | Git repository folder structure |  | All Team | In-Progress |  | 2022-11-08 | 2022-11-08
|  | Database access and user creation (Local) |  | All Team | In-Progress |  | 2022-11-04 | 2022-11-07
|  | Finalize the database tables (Use case) |  | All Team | Completed |  | 2022-11-04 | 2022-11-04
M2 | Admin Module (Front-End) | Design login UI for employees |  | Nitin | In-Progress |  | 2022-11-03 | 2022-11-07
|  | Design Registration UI for hospital employee (by admin only) |  | Nitin | In-Progress |  | 2022-11-04 | 2022-11-07
|  | Forget password UI |  | Nitin | In-Progress |  | 2022-11-08 | 2022-11-08
|  | Reset password UI |  | Nitin | In-Progress |  | 2022-11-08 | 2022-11-08
|  | show all the users with their details and status (Patient+Employee) |  | Nitin | In-Progress |  | 2022-11-09 | 2022-11-09
|  | disable or unlock a user through the grid (Patient+Employee) |  | Nitin | In-Progress |  | 2022-11-09 | 2022-11-09
|  | Add Sign out functionality (redirect to homepage) |  | Nitin | In-Progress |  | 2022-11-09 | 2022-11-09
| Admin Module(Backend) | CRUD APIs for all employees | Rest end points | Surabhi | In-Progress |  | 2022-11-03 | 2022-11-03
end point security
Exception handling
Junit Test cases
|  | Update Status API | Update end point | Surabhi | In-Progress |  | 2022-11-03 | 2022-11-03
|  | Login verification API |  | Surabhi | In-Progress |  | 2022-11-04 | 2022-11-04
|  | Change/Reset Password API |  | Surabhi | In-Progress |  | 2022-11-04 | 2022-11-08
|  | Forgot Password using OTP API |  | Surabhi | In-Progress |  | 2022-11-04 | 2022-11-08
|  | Find Employee by First Name API |  | Surabhi | In-Progress |  | 2022-11-07 | 2022-11-08
|  | Send Email to specific Employee |  | Surabhi | In-Progress |  | 2022-11-07 | 2022-11-08
M3 | User Module (Front-End) | Design login UI for patients |  | Anil | In-Progress |  | 2022-11-03 | 2022-11-07
|  | Design Registration UI for patients |  | Anil | In-Progress |  | 2022-11-03 | 2022-11-07
|  | Forget password UI |  | Anil | In-Progress |  | 2022-11-08 | 2022-11-08
|  | Reset password UI |  | Anil | In-Progress |  | 2022-11-08 | 2022-11-08
|  | Add Sign out functionality (redirect to homepage) |  | Anil | In-Progress |  | 2022-11-09 | 2022-11-09
| User Module (Back-End) | Register Patient API |  | Mustaq | In-Progress |  | 2022-11-03 | 2022-11-04
|  | Login Patient API |  | Mustaq | In-Progress |  | 2022-11-04 | 2022-11-04
|  | Forgot Password API |  | Mustaq | In-Progress | 90% | 2022-11-07 | 2022-11-08
|  | Change/Reset Password API |  | Mustaq | In-Progress | 90% | 2022-11-07 | 2022-11-08
M4 | Patient Module (Backend) | Add Patient Details |  | Mustaq |  |  | 2022-11-11 | 2022-11-14
|  | Display Patient Details |  | Mustaq |  |  | 2022-11-11 | 2022-11-14
|  | Update Patient Details (Nurse or Physician) |  | Mustaq |  |  | 2022-11-12 | 2022-11-14
|  | Add Patient Visit Details |  | Mustaq |  |  | 2022-11-13 | 2022-11-14
| Patient Module(Front-End) | Search and select patient UI |  | Anil |  |  | 2022-11-11 | 2022-11-14
|  | UI to capture Demographics |  | Anil |  |  | 2022-11-11 | 2022-11-14
|  | UI to capture allergies |  | Anil |  |  | 2022-11-12 | 2022-11-14
M5 | Patient Visit Module (Front-End) | Search and select patient UI |  | Anil |  |  | 2022-11-14 | 2022-11-17
|  | UI to capture patient visit details |  | Anil |  |  | 2022-11-14 | 2022-11-17
|  | Diagnosis sub-section UI |  | Anil |  |  | 2022-11-15 | 2022-11-17
|  | Procedures sub-section UI |  | Anil |  |  | 2022-11-15 | 2022-11-17
|  | Medication sub-section UI |  | Anil |  |  | 2022-11-16 | 2022-11-17
|  | View saved patient details and edit option for the same |  | Anil |  |  | 2022-11-17 | 2022-11-17
| Patient Visit Module (Back-End) | Patient visit detail service |  | Mustaq |  |  | 2022-11-15 | 2022-11-17
M6 | Inbox Module(Backend) | CRUD API for appointment (by employee) |  | Surabhi |  |  | 2022-11-11 | 2022-11-17
|  | Create- table for notes |  | Surabhi |  |  | 2022-11-11 | 2022-11-17
|  | send notes |  | Surabhi |  |  | 2022-11-14 | 2022-11-17
|  | reply the note |  | Surabhi |  |  | 2022-11-14 | 2022-11-17
|  | delete note |  | Surabhi |  |  | 2022-11-14 | 2022-11-17
|  | View sent notes(sorted on basis of timeand date) |  | Surabhi |  |  | 2022-11-14 | 2022-11-17
|  | Exception handle |  | Surabhi |  |  | 2022-11-14 | 2022-11-17
|  | get upcoming and declined appointment(for patient) |  | Surabhi |  |  | 2022-11-15 | 2022-11-17
|  | Declined appointment notification |  | Surabhi |  |  | 2022-11-15 | 2022-11-17
|  | appointment book ,cancel,modified email sent to patient |  | Surabhi |  |  | 2022-11-16 | 2022-11-17
|  | patient can book data collection appointment |  | Surabhi |  |  | 2022-11-16 | 2022-11-17
| Inbox Module(UI) | Add ‘Appointment Scheduling” button on dashboard and create scheduling page |  | Nitin |  |  | 2022-11-11 | 2022-11-17
|  | Add ‘Data Collection Appointment Scheduling” button on its dashboard |  | Nitin |  |  | 2022-11-11 | 2022-11-17
|  | Add View Schedular’ button |  | Nitin |  |  | 2022-11-14 | 2022-11-17
|  | View/Add / Edit/ Delete Meeting as per availability of the appointment should be checked on the Physician selected . |  | Nitin |  |  | 2022-11-15 | 2022-11-17

## Admin Module
Module | Functionality | Sub-Tasks | Member's Name | Status | Completion % | Start Date | End Date
Admin Module (Front-End) | Design login UI for employees |  | Nitin | In-Progress |  | 2022-11-03 | 2022-11-07
| Design Registration UI for hospital employee (by admin only) |  |  | In-Progress |  | 2022-11-04 | 2022-11-07
| Forget password UI |  |  | In-Progress |  | 2022-11-08 | 2022-11-08
| Reset password UI |  |  | In-Progress |  | 2022-11-08 | 2022-11-08
| show all the users with their details and status (Patient+Employee) |  |  | In-Progress |  | 2022-11-09 | 2022-11-09
| disable or unlock a user through the grid (Patient+Employee) |  |  | In-Progress |  | 2022-11-09 | 2022-11-09
| Add Sign out functionality (redirect to homepage) |  |  | In-Progress |  | 2022-11-09 | 2022-11-09
Admin Module(Backend) | CRUD APIs for all employees | Rest end points | Surabhi | Completed | 100 | 2022-11-03 | 2022-11-03
|  | Default password email |  | In-Progress | 50
|  | Welcome email for new user |  | Completed
| Update Status API | Update end point |  | Completed | 100 | 2022-11-03 | 2022-11-03
|  | Mail notification |  | Completed | 10
| Login verification API | Username and password Authentication |  | In-Progress | 50 | 2022-11-04 | 2022-11-04
| Change/Reset Password API | End point for password reset using old password |  | In-Progress | 100 | 2022-11-04 | 2022-11-08
| Forgot Password using OTP API | End point |  | Completed | 100 | 2022-11-04 | 2022-11-08
|  | OTP generation |  | Completed | 100
|  | send OTP over email |  | Completed | 100
| Find Employee by First Name API |  |  | Completed |  | 2022-11-07 | 2022-11-08
| Send Email to specific Employee |  |  | In-Progress |  | 2022-11-07 | 2022-11-08
| Common Tasks | end point security |  | Pending
|  | Exception handling |  | Pending
|  | Junit Test cases |  | Pending

## User Module
Module | Functionality | Sub-Tasks | Member's Name | Status | Start Date | End Date
User Module (Front-End) | Design login UI for patients | Login screen | Anil | Complete | 2022-11-03 | 2022-11-07
|  | Validation |  | In-Progress
|  | Integration with backend |  | Complete
|  | Redirection Page |  | Pending
| Design Registration UI for patients | Registration screen |  | In-Progress | 2022-11-03 | 2022-11-07
|  | Integration with backend |  | In-Progress
|  | Redirection Page |  | Pending
| Forget password UI |  |  | In-Progress | 2022-11-08 | 2022-11-08
| Reset password UI |  |  | In-Progress | 2022-11-08 | 2022-11-08
| Add Sign out functionality (redirect to homepage) |  |  | Pending | 2022-11-09 | 2022-11-09
User Module (Back-End) | Register Patient API | End point | Mustaq | Complete | 2022-11-03 | 2022-11-04
|  | Send welcome email |  | Complete
| Login Patient API |  |  | Complete | 2022-11-04 | 2022-11-04
| Forgot Password API | End point |  | Complete | 2022-11-07 | 2022-11-08
|  | Send default password email |  | Complete
| Get Patient API |  |  | Complete
| Get logged in patient |  |  | Complete
| Change/Reset Password API |  |  | Complete | 2022-11-07 | 2022-11-08
| Junit Test Cases |  |  | Pending
| Exception Handling |  |  | In-Progress
| End Point Security |  |  | In-Progress

## Tasks
Functionality | SubFunctionality | Member's Name | Status | Start Date | End Date
ER Diagram | Create ER Diagram | Anil | Done | 2022-04-11 | 2022-04-11
Patient/Admin Module | Patient's Registration Service | Mustaq | In Progress | 2022-02-11
| Patient's Registration UI | Anil | In Progress | 2022-02-11
| Patient Registration Integration | Mustaq/Anil |  | 2022-02-11
| Physician/Nurse Registration Service | Surabhi | In Progress | 2022-02-11
| Physician/Nurse Registration UI | Nitin | In Progress
| Physician/Nurse Registration Integration | Surabhi/Anil | In Progress
| Login screen(Patient) Service | Mustaq | In Progress
| Login screen(Physician/Nurse/Admin) Service | Surabhi
| Login screen(Physician/Nurse/Admin) UI | Nitin | In Progress
| Login screen(Physician/Nurse/Admin) Integration | Surabhi/Nitin
| Change Password Service | Surabhi | In Progress
| Change Password UI | Nitin
| Change Password Integration | Surabhi/Nitin
| Forget password Service | Surabhi
| Forget password UI | Nitin
| Forget password Integration | Surabhi/Nitin
| Patient demographic details Service | Mustaq
| Patient demographic details add UI | Anil
| Patient demographic details show UI | Anil
| Patient demographic details Integration | Mustaq/Anil
| Patient diagnosis details Service | Surabhi
| Patient diagnosis details UI | Anil
| Patient diagnosis details Integration | Surabhi/Anil
| Patient Procedure and medication Service | Mustaq
| Patient Procedure and medication UI | Nitin
| Patient Procedure and medication Integration | Mustaq/Nitin
Scheduling Module | Appointment schedule Service
Appointment schedule UI
Appointment schedule Integration
Patient schedule data collection appointment Service
Patient schedule data collection appointment UI
Patient schedule data collection appointment Integration
View schedule Physician Service
View schedule Physician UI
View schedule Physician Integration
Admin patient user management Service
Admin patient user management UI
Admin patient user management Integration
Hospital user Module | Hospital user inbox Service
Hospital user inbox UI
Hospital user inbox Integration
Patient Module | Patient inbox Service
Patient inbox UI
Patient inbox Integration